## 0.APQP GRC
|  |  | APQP Gate Release Checklist (APQP GRC) | [8 empty] | GATES RACI CHART RESPONSIBLE ACCOUNTABLE SUPPORTING CONSULTED INFORMED |  |  |  |  | Not started | Open | OK | Automotive | TBD | TBD
[17 empty] | Launched | Conditionally closed | Cond. OK | Non-Automotive | PREMO Mediterranée | Da Nang
[17 empty] | Completed |  | N/A |  | PREMO Wuhu | Málaga
| Project Manager : | Name Surname |  | Project Name: |  | Project Name: | [10 empty] | Approved |  |  |  |  | Tangier
| PREMO P/N: | X-12345-678 |  | Part Description: |  | Part Description: | [10 empty] | Conditional Approved |  |  |  |  | Wuhu
| Customer P/N: | RT23423AA |  | Customer Name: | Name of the customer | Customer Name: | [10 empty] | Rejected
| Samples Center: |  |  | Category: |  | Category:
| Manuf. Center: |  |  | Last Rev. Date: |  | Last Rev. Date:
1 | FEASIBILITY FOR OPPORTUNITIES - QUALITY GATE LEAD: BUSINESS UNIT DIRECTOR |  |  |  |  | Action item/Deliverable | Status | Planned Date | Link to deliverable | Remarks / Gaps | Criteria for acceptance | Responsible | Accountable | Supporting | Consulted | Informed
Feasibility for Opportunities | 1.1 | CIR (Customer Input Requirements) |  |  |  | CIR Form (Technical/Commercial) |  |  |  |  | 1.- All mandatory fields filled in 2.- Reviewed by BU Director | Key Account Manager | BU Director | Field Application Engineer | Category Design Leader | R&D Director / Corporate Quality Director
| 1.2 | Technical Feasibility |  |  |  | Technical Feasibility Analysis |  |  |  |  | 1.- Technical feasibility analysis result is determined (OK/NG): product/process requirements cross check and estimated margin (quick costing done) 2.- Reviewed by CDL | Field Application Engineer | Key Account Manager | Product design engineer / Corporate controller | Category Design Leader | BU Director
| 1.3 | Project Committe Acceptance |  |  |  | 1.- Project Cttee Acceptance Submission 2.- Gate 1 Release Team definition and design/samples/manuf center definition inside PCA submission |  |  |  |  | 1.- Technical feasibility analysis result must be OK 2.- All mandatory fields filled in 3.- Reviewed by CDL | 1.- Key Account Manager 2.- RD Director, Purchasing Director, Quality Director, Plant Manager, Operations Director | BU Director | Field Application Engineer | CEO | CFO / Sr. Management Team / Project Manager
| 1.4 | Previous DFMEA and Lessons Learnt |  |  |  | DFMEA and Lessons Learn up to date of the product family |  |  |  |  | 1.- Family FMEA is reviewed by FAE | Field Application Engineer | R&D Manager | Category Design Leader | Project Quality Engineer | Corporate Quality Director
| 1.5 | Technical definition |  |  |  | 1. Design Concept 2. BOM & Process Flowchart (inside PDCC) 3. Preliminary Datasheet |  |  |  |  | 1.- Design Concept: all mandatory fields fileld in (BOM and Flowchart) 2.- BOM & Process Flowchart in PDCC matching with Design Concept 3.- Preliminary Datasheet is complete and reviewed by RD Manager/Supervisor/CDL | Product design engineer | Field Application Engineer | Process design engineer | Category Design Leader | R&D Director / Key Account Manager / Purchasing Officer / Project Quality Engineer
| 1.6 | PDCC completion |  |  |  | PDCC |  |  |  |  | 1.- All mandatory fields filled in 2.- Reviewed by Functional Managers (Purchasing, RD) 3.- Reviewed by Corporate controlling for consistency | PDCC team defined inside PDCC | Key Account Manager | Field Application Engineer | Corporate Controller | Corporate Controller / BU Director
| 1.7 | Samples WI |  |  |  | Samples WI (A) |  |  |  |  | 1.- All materials of BOM and process steps inside PDCC/Design Concept are included. Visuals may be provided with 3D drawing snapshots at this stage. 2.- Quality criteria for each step and technology to be used is defined. No need to specify process parameters, only record them in SIR later. 3.- Reviewed by RD Supervisor/Manager | Product design Engineer | R&D Manager | Process design Engineer | Prototype Engineer | Field Application Engineer / Prototype Engineer / Sample Leader / Project Quality Inspector
| 1.8 | Sample Production |  |  |  | 1. Sample Production Plan 2. SIR |  |  |  |  | 1.- Sample Production Plan: all mandatory fields are filled in and reviewed by FAE/RD Manager 2.- SIR: all mandatory fields are filled in (including 3rd and extreme test/disassembly) and reviewed by Product design engineer | 1.- Product design engineer 2.- Prototype Engineer | 1.- Field Application Engineer 2.- Product design engineer | Process design Engineer | R&D Manager | Field Application Engineer
| 1.9 | Customer Feedback |  |  |  | Customer feedback: Email, report summary |  |  |  |  | Evidence is available | Key Account Manager | BU Director | Category Design Leader / Field Application Engineer | Product design engineer | R&D Manager
| 1.10 | Feasibility bundle (*) |  |  |  | Close Feasibility Bundle (project plan inside) |  |  |  |  | 1.- Close Feasibility Bundle result is determined (OK/NG) based on timeline, pricing and technical feasibility by customer. 2.- Close Feasibility Bundle is reviewed by senior management team (RD Director/QA Director/Plant Manager/Purchasing Director) | Project Manager | Key Account Manager | R&D Manager | R&D Director / Plant Manager | BU Director / Plant Manager
| 1.11 | Customer Agreement - LON (*) |  |  |  | 1.- RFQ Cttee Submission 2.- LON |  |  |  |  | 1.- Close Feasibility Bundle result is OK from customer and internal review. 2.- RFQ Cttee Submission conditions match with LON conditions 3.- LON is reviewed by Corporate Controlling 4.- LON is signed by CFO/CEO | Key Account Manager | BU Director | Project Manager | Corporate Controller | Sr. Management Team / Project Manager
| PHASE VALIDATION RESULT |  |  | PHASE LEAD
| Release Status: |  | Not started | BU Director
Released by:
Release Date:
2 | DESIGN VALIDATION - QUALITY GATE LEAD: RD DIRECTOR |  |  |  |  | Action item/Deliverable | Status | Planned Date | Link to deliverable | Remarks / Gaps | Criteria for acceptance | Responsible | Accountable | Supporting | Consulted | Informed
Design Validation | 2.1 | Team Definition |  |  |  | Gate Release Team defined in GRC Form and in PDCC for all the gates (adding 2, 3 and 4) |  |  |  |  | 1.- Gate Release Team for all gates defined (adding 2, 3 and 4) 2.- Team definition coordinated with functions and communicated to responsibles and management | Project Manager | Plant Manager | R&D Manager / QA Manager / Engineering Manager / Purchasing Manager / Production Manager/ Maintenance Manager / Supply Chain Manager | Operations Director / R&D Director / QA Director / Purchasing Director | Sr. Management Team / Plant Management Team
| 2.2 | Project Master Plan |  |  |  | PMP (Project Master Plan): 1. DV 2. PV 3. QTP 4. Supplier validation 5. Customer milestones vs Premo milestones |  |  |  |  | 1.- All plans are available 2.- Customer milestones are achievable 3.- Plans are reviewed by Functional managers | 1. Product design Engineer 2. Industrial Engineer 3. Project Quality Engineer 4. Purchasing Officer | Project Manager | 1.- Field Application Engineer 2.- Process design Engineer 3.- Laboratory Engineer 4.- Supplier Quality Engineer | 1. R&D Manager 2. Engineering Manager 3. QA Manager 4. Purchasing Manager 5.- Key Account Manager | R&D Director / BU Director / QA Director / Purchasing Director / Plant Manager / Key Account Manager
| 2.3 | Launch the investment |  |  |  | 1.- CAPEX Cttee Submission 2.- Investment system release |  |  |  |  | 1.- CAPEX Cttee Submission: all mandatory data is filled in (project introduction, technical presentation, investment list, economical analysis) and is presented in Monthly CAPEX meeting to Senior Mgmt 2.- Investment system release: CAPEX Cttee Submission is approved by CEO and CFO and CO order released for the approved amount | 1.- Project Manager 2.- Corporate controller | 1.- RD Director 2.- Project Manager | Quality Director / Purchasing Director / R&D Director | CEO / CFO | Purchasing Manager / Quality Manager / Plant Finance Manager / Plant Manager
| 2.4 | Project Kick off |  |  |  | Email or MoM |  |  |  |  | MoM is available | Project Manager | Plant Manager | R&D Manager / QA Manager / Engineering Manager / Purchasing Manager / Production Manager/ Maintenance Manager / Supply Chain Manager | BU Director / Operations Director | Key Account Manager
| 2.5 | Design Concept Review |  |  |  | 1.- Design Concept 2.- BOM (inside PDCC) 3.- Process Flowchart |  |  |  |  | 1.- Design Concept: all mandatory fields fileld in (BOM and Flowchart) 2.- BOM & Process Flowchart in PDCC matching with Design Concept 3.- Process Flowchart defines all steps of the process (manufacturing and control) | 1 &2 .- Product design engineer 3.- Process design engineer | R&D Manager | 1 &2.- Process design engineer 3.- Industrial engineer | Category Design Leader | Project Manager / Purchasing Manager / R&D Director
| 2.6 | DFMEA and Preliminary PFMEA |  |  |  | 1.- DFMEA 2.- PFMEA |  |  |  |  | 1.- DFMEA is including all customer requirements and PFMEA is including all process steps and product characteristics 2.- There is always action when RPN is higher than defined limit (100) 3.- Both FMEAs are reviewed by Functional Manager and CDL | 1. Product design Engineer 2. Process design Engineer | Project Quality Engineer | Coporate QMS / Field Application Engineer | Corporate Quality Engineer / R&D Manager / Category Deisgn Leader / Engineering Manager | Engineering Manager/ Production Manager/ Plant Quality Manager / Project Manager
| 2.7 | Product & Process Technical Definition: |  |  |  | 1. Product Datasheet and Raw material specifications 2. Process Specifications |  |  |  |  | 1.- Product Datasheet and Raw material specifications: all mandatory fields are filled in and document is reviewed by RD Manager 2.- Process Specifications: all process steps in flow chart are included and full requirements of process are defined (controls, manufacturing parameters, technology to be used, cycle time and others) | 1.- Product design engineer 2.- Process design Engineer | R&D Manager | Category Design Leader | R&D Director | KAM/ Engineering Manager / Project Manager / R&D Director / Corporate Quality System
| 2.8 | Preliminary Control Plan |  |  |  | Control Plan |  |  |  |  | 1.- Control plan: all process steps, product and process characteristics are covered 2.- Control plan is reviewed by Corporate Quality Engineer, Engineering Manager and RD Manager | Project Quality Engineer | Corporate Quality Engineer | Process design engineer / Industrial engineer | R&D Manager / Engineering Manager | Plant Quality Manager / Production Manager / Engineering Manager / R&D Manager
| 2.9 | Preliminary Work Instruction |  |  |  | Samples WI (B) |  |  |  |  | 1.- All materials of BOM and process steps inside PDCC/Design Concept are included. Visuals are provided with pictures of real parts. 2.- Quality criteria and process parameters for each step and technology to be used is defined 3.- Reviewed by RD Supervisor/Manager | Process Design Engineer | R&D Manager | Industrial Engineer / Manufacturing Engineer | Prototype Engineer | Prototype Engineer / Sample Leader / Project Quality Inspector
| 2.10 | Qualification Test Plan (QTP) |  |  |  | Qualification Test Plan |  |  |  |  | 1.- All tests compliant to AECQ-200 and specific customer requirements are considered 2.- Timeline with quantities needed and planned dates for tests is available and can match planned schedule for the phase 3.- QTP plan is reviewed by Project Manager and QA Manager | Project Quality | QA Manager | Product design Engineer / Category Design Leader | Customer / Project Manager | Project Manager Lab Engineer
| 2.11 | DV Bundle (*) |  |  |  | Close DV Bundle: 1. Raw material inspection report (all sources) 2. Process DOE results (all sources - fix parameters) 3. Limit tolerance check (max, nom, min, for all sources) 4. QTP report (all sources - fix parameters) |  |  |  |  | 1.- All mandatory fields are filled in 2.- Manufacturability assessment result is pass (process DOE) 3.- Limit tolerance is fixed for each RM 4.- QTP report result is passed for all tolerances of at least one source for each RM | 1. IQC inspector 2. Prototype Engineer 3. Process Designer 4. Lab. Engineer | 1. Project Quality Engineer 2. Process Design Engineer 3. R&D Manager 4. Project Quality Engineer | Corporate QMS / Corporate Quality Engineer / Category Design Leader | R&D Director / QA Director | Project Manager KAM
| 2.12 | Product datasheet and process specifications |  |  |  | 1.- Product datasheet and Raw material specifications 2.- BOM and Packaging Agreement 3.- Process specifications |  |  |  |  | 1.- Product Datasheet and Raw material specifications: all mandatory fields are filled in and document is reviewed by RD Manager. Parameters should match with validated QTP results. 2.- BOM updated according with QTP results and Packaging agreed with customer 3.- Process Specifications: all process steps in flow chart are included and full requirements of process are defined (controls, manufacturing parameters, technology to be used, cycle time and others). Parameters should match with validated QTP results. | 1 & 2.- Product design Engineer 3.- Process design Engineer | R&D Manager | Corporate QMS | R&D Director / QA Director | Project Manager
| 2.13 | PFMEA |  |  |  | PFMEA |  |  |  |  | 1.- PFMEA is including all process steps and product characteristics 2.- There is always action when RPN is higher than defined limit (100) 3.- PFMEA is reviewed by Functional Manager and CDL | Process Design Engineer | Project Quality Engineer | Industrial Engineer / Manufacturing Engineer | Corporate Quality Engineer / R&D Manager / Category Deisgn Leader / Engineering Manager | Engineering Manager/ Quailty Manager/ Production Manager / R&D Manager / Project Manager
| 2.14 | PDCC & Profitability reviewed |  |  |  | PDCC |  |  |  |  | 1.- All mandatory fields filled in 2.- Reviewed by Functional Managers (Purchasing, RD) 3.- Reviewed by Corporate controlling for consistency 4.- CM matches RFQ PDCC and in case it doesn't, then there is an action plan approved by management | PDCC team defined inside PDCC | Project Manager | R&D Director / Purchasing Director / Plant Manager | Corporate controller | BU Director
| 2.15 | SOCO for Raw Material (*) |  |  |  | SOCO for Raw Material |  |  |  |  | 1. Supplier is sourceable (already approved, no NBH or potential supplier audit passed) 2. Supplier Technical Feasibility Gate to be closed before nomination 3. Samples delivered and test passed 4. RM APQP open in VEGA for all new parts 5. GTC and Suppplier Quality Agreement signed by all suppliers 6.- At least 3 quotes are presented and the quotation nominated is matching the target cost in PDCC 7.- Cost breakdown is available for presented quotes 8.- Detailed timeline is available and complies with project timing requirements | Purchasing Officer | Purchasing Manager | Product design Engineer / SQE / Corporate controller | Purchasing Director | Project Quality Engineer / Project Manager
| 2.16 | SOCO for Machine & Equipment (internal - no sourcing decision to supplier) (*) |  |  |  | SOCO for Machine & Equipment (internal only - no sourcing decision to supplier) |  |  |  |  | 1. Supplier Technical Feasibility vs Process specification is passed 2.- At least 3 quotes are presented and the quotation nominated is matching the target CAPEX in PDCC 3.- Cost breakdown is available for presented quotes 4.- Detailed timeline is available and complies with project timing requirements | Industrial Engineer | Engineering Manager | Process design Engineer / Corporate controller | Operations Director / Plant Manager | Project Quality Engineer / Project Manager
| PHASE VALIDATION RESULT |  |  | PHASE LEAD
| Release Status: |  | Not started | Corp RD Director
Released by:
Release Date:
3 | INDUSTRIALIZATION - QUALITY GATE LEAD: PLANT MANAGER |  |  |  |  | Action item/Deliverable | Status | Planned Date | Link to deliverable | Remarks / Gaps | Criteria for acceptance | Responsible | Accountable | Supporting | Consulted | Informed
Industrialization | 3.1 | Launch the investment |  |  |  | 1.- CAPEX Ctte Submission 2.- Investment system release |  |  |  |  | 1.- CAPEX Cttee Submission: all mandatory data is filled in (project introduction, technical presentation, investment list, economical analysis) and is presented in Monthly CAPEX meeting to Senior Mgmt 2.- Investment system release: CAPEX Cttee Submission is approved by CEO and CFO and CO order released for the approved amount | 1.- Project Manager 2.- Corporate controller | 1.- Plant Manager 2.- Project Manager | Quality Director / Purchasing Director / Operations Director | CEO / CFO | Purchasing Manager / Quality Manager / Engineering Manager / Plant Finance Manager
| 3.2 | Definitve Production Layout |  |  |  | Full Operating Layout |  |  |  |  | 1.- All machines, equipments and accessories of the line are depicted in the production layout and consistent with the process flow chart. 2.- All material movements are depicted in the layout and consistent with the process flow chart. 3.- All direct employees operating the line are depicted in the layout and consistent with the process flow chart. 4.- Full Operating Layout is reviewed by Plant Manager | Industrial Engineer | Engineering Manager | Facilities Manager | Plant Manager | Facilities Mgr. / Production Mgr. / HSE Supervisor
| 3.3 | Equipment installation |  |  |  | 1.- FAT Report 2.- Installation checklist |  |  |  |  | 1.- FAT Report: all mandatory fields are filled in (machinery construction and assembly is fully completed and all functions implemented) and reviewed by Engineering Manager 2.- Installation checklist: all mandatory fields are filled in (neumatics, electricity, oil and other installations completed successfully) and reviewed by Facility/Engineering Manager | 1.- Industrial Engineer 2.- Maintenance Engineer | Engineering Manager | Facilities Manager/ Maintenance Mgr. / Supply Chain Mgr. | Plant Manager | Facilities Mgr. / Production Mgr. / HSE Supervisor
| 3.4 | Raw Material approved (PPAP) & Capacity Verification (Run@Rate) |  |  |  | RM PPAP approved (all suppliers) |  |  |  |  | 1.- Run and Rate's score is passed vs PDCC requested capacity 2.- QTP in DV passed for the material (DV Bundle) 3.- Control plan from supplier is audited and approved by Premo 4.- Supplier datasheet matching with Premo RM Specification and reviewed and approved by Premo | Project Quality Engineer | Purchasing Officer | Supply Chain Manager / Engineering Manager / R&D Manager | SQE | Supply Chain Manager / QA Manager / Corporate Quality Systems / Project Manager / Purchasing Manager
| 3.5 | Material Reception & Delivery |  |  |  | 1. WI for Packaging (FGs in pallets) / shipment preparation (Family) 2. WI for Storage (Family) 3. WI for Incoming Inspection 4. Tools for incoming inspection |  |  |  |  | 1.- WI for Packaging: Family WI is updated and reviewed by Supply Chain Manager 2.- WI for Storage: Family WI is updated and reviewed by Supply Chain Manager 3.- WI for Incoming Inspection: all special characteristics in RM Specification are mentioned and controlled with proper equipment and reviewed by QA Manager | 1. Warehouse Supervisor 2. Warehouse Supervisor 3. Project Quality Inspector 4. Industrial Engineer | 1. Supply Chain Manager 2. Supply Chain Manager 3 &4. Project Quality Engineer | Purchasing Officer / Product design Engineer | 1, 2 & 4.- Quality Control Engineer 3. SQE / IQC inspector | Production Manager Supply Chain Manager Engineering Manager QA Manager
| 3.6 | IQ (Installation Qualification) |  |  |  | IQ Bundle |  |  |  |  | 1.- Pre-installation verification: overall inspection without damages/abnormalities, no missing components 2.- Installation verification: power on/off, basic setup check, components/equipments status 3.- Functional verification: all features present and working, worst case check | Industrial Engineer | Engineering Manager | Process Design Engineer / Maintenance Engineer | Plant Manager / Finance Manager | Production Manager QA Manager
| 3.7 | OQ (Operation Qualification) |  |  |  | OQ Bundle: 1. Setup Work Instructions & records 2. Spare part list 3. Preventive Maintenance Plan and WI 4. Machine R@R |  |  |  |  | 1.- Setup Work Instructions & records: all steps to setup the machine are mentioned and well documented and reviewed by Maintenance Manager 2.- Spare part list: all needed spare parts are listed and reviewed by Maintenance Manager 3.- Preventive Maintenance Plan and WI: all items that are needed are mentioned and reviewed with Maintenance Manager 4.- Machine R@R: result of OEE pass versus defined PDCC target and reviewed by Engineering Manager | 1, 2, 3. Maintenance Engineer 4. Industrial Engineer | Engineering Manager | Process Design Engineer | Plant Manager / Maintenance Manager | R&D Manager Project Quality Engineer QA Manager Production Manager
| 3.8 | PQ (Performance Qualification) |  |  |  | PQ Bundle: 1.- Machine setup and DOE 2. MSA (all stations GO/NG, fixed process parameters) 3. Gage R&R (all manufacturing processes and test processes with numerical result, fixed process parameters) |  |  |  |  | 1.- MSA (all stations GO/NG, fixed process parameters): result is pass. 2.- Gage R&R (all manufacturing processes and test processes with numerical result, fixed process parameters): result is pass. | 1. Industrial Engineer 2, 3. Project Quality Engineer | Engineering Manager | Manufacturing Engineer / Quality Control Engineer | Plant Manager / QA Manager | Productoin Manager QA Manager Maintenance Manager
| 3.9 | Definitive Process Documentation |  |  |  | 1. PFMEA 2. Control Plan |  |  |  |  | 1.- PFMEA is including all process steps and product characteristics 2.- There is always action when RPN is higher than defined limit (100) 3.- PFMEA is reviewed by Functional Manager and CDL 4.- Control plan: all process steps, product and process characteristics are covered 5.- Control plan is reviewed by Quality Manager, Engineering Manager and Production Manager | 1. Industrial Engineer 2. Project Quality Engineer | 1. Project Quality Engineer 2. Quality Control Engineer | Corporate Quality Systems / Process Design Engineer / Manufacturing Engineer / Maintenance Engineer | QA Manager | Production Manager QA Manager Engineering Manager Maintenance Manager
| 3.10 | Wis and Training |  |  |  | 1. Manufacturing Work Instructions 2. Training Plan and Training Matrix (Production / Quality) |  |  |  |  | 1.- All materials of BOM and process steps inside PDCC/Design Concept are included. Visuals are provided with pictures of real parts. 2.- Quality criteria and process parameters for each step and technology to be used is defined. Visuals of NG and Good parts are clearly defined with pictures of real parts. 3.- The set of toolings and parameters to operate each station is clearly defined and aligned with control plan, stablishing a 6S standard for compliance 4.- The sequence of operation in each station of the process is defined in detail and with supportive pictures to let operator understand (specially in manual stations) 5.- Reviewed by Production Manager | 1. Manufacturing Engineer 2. Production Supervisor / Quality Control Engineer | 1. Production Manager 2. Production Manager / QA Manager | 1. Industrial Engineer / Sample Leader 2. HSE Supervisor / HR Supervisor | 1. Production Supervisor 2. Quality Supervisor | QA Manager / Engineering Manager / HR Manager
| 3.11 | Line Release Audit - Including New Equipment, Tooling, and Test Equipment Release (*) |  |  |  | Line Release Report: 1. Run @ Rate 2. Process Audit (VDA 6.3) 3. Closing Meeting (Line Release Report should be available) 4. Action plan approval and launch (2 weeks max timing) |  |  |  |  | 1.- Run & Rate result is pass 2.- Process Audit result is pass 3.- Line Release Report is signed by Plant Manager and agreed by all Functional managers in the plant | 1. Industrial Engineer / Manufacturing Engineer 2. Project Quality Engineer 3. QA Manager 4. Engineering Manager | 1. Engineering Manager / Production Manager 2. QA Manager 3 & 4. Project Manager | Corporate QMS / Quality System Engineer | Plant Manager / Quality Director | Supply Chain Manager Production Manager Maintenance Manager Corporate Controller Plant Finance Manager Plant Manager Quality Director BU Director
| 3.12 | QTP batch manufacturing with full conditions |  |  |  | 1. QTP batch manufacturing 2. QTP test 3. QTP Report |  |  |  |  | 1.- QTP Report result is pass 2.- QTP Report is containing all test results from the tests highlighted in QTP plan 3.- QTP Report contains pictures and measurements of the real parts for each test and the parts are physically available for inspection if requested | 1. Industrial Engineer 2 & 3. Lab. Engineer | Project Quality Engineer | QA Manager Corporate Quality Systems Project Manager | Plant Manager / Quality Director | Key Account Manager R&D Manager & Director Maintenance Manager Plant Manager QA Director Project Manager
| 3.13 | FMEA and Control Plan final review and release |  |  |  | 1. PFMEA 2. Control Plan |  |  |  |  | 1.- PFMEA is including all process steps and product characteristics 2.- There is always action when RPN is higher than defined limit (100) 3.- PFMEA is reviewed by Functional Manager and CDL 4.- Control plan: all process steps, product and process characteristics are covered 5.- Control plan is reviewed by Quality Manager, Engineering Manager and Production Manager | 1. Industrial Engineer 2. Project Quality Engineer | 1. Project Quality Engineer 2. Process Quality Engineer | Corporate Quality Systems / Process Design Engineer / Manufacturing Engineer / Maintenance Engineer | QA Manager | Production Manager QA Manager Engineering Manager Maintenance Manager
| 3.14 | PDCC & Profitability reviewed - Fix route and scrap |  |  |  | PDCC |  |  |  |  | 1.- All mandatory fields filled in 2.- Reviewed by Functional Managers (Purchasing, RD) 3.- Reviewed by Corporate controlling for consistency 4.- CM matches RFQ PDCC and in case it doesn't, then there is an action plan approved by management | PDCC team defined inside PDCC | Project Manager | R&D Director / Purchasing Director / Plant Manager | Corporate controller | BU Director
| 3.15 | PPAP Approval (PSW Signed) - Received & Reviewed (*) |  |  |  | PPAP |  |  |  |  | 1.- PPAP is approved by customer 2.- PPAP is reviewed by all Functional Managers 3.- PPAP is signed by Plant Manager/QA Director | Project Quality Engineer | QA Manager | Engineering Manager / Corporate Quality Systems / Project Manager | Plant Manager / Quality Director | Key Account Manager Engineering Manager Production Manager Quality Manager Supply Chain Manager Maintenance Manager Quality Director
| PHASE VALIDATION RESULT |  |  | PHASE LEAD
| Release Status: |  | Not started | Plant Manager
Released by:
Release Date:
4 | SOP + 6 MONTHS - QUALITY GATE LEAD: PROJECT MANAGER |  |  |  |  | Action item/Deliverable | Status | Planned Date | Link to deliverable | Remarks / Gaps | Criteria for acceptance | Responsible | Accountable | Supporting | Consulted | Informed
SOP + 6 Months | 4.1 | Quality Review (*) |  |  |  | SOP Review format (Int/Ext Claims, Safe launch/Quality walls, Achievement vs LON, Deliveries vs orders, Actual profitability vs PDCC) |  |  |  |  | 1.- No claims in 6 months after project start or in a period of 6 months from last claim received 2.- Achievement matches with LON and deliveries are done according to orders without delay 3.- CM in PDCC matches CM in RFQ PDCC | 1.- Quality Control Engineer / Customer Quality Engineer | 1.- QA Manager | 1.- Quality Director / Plant Manager | CEO/CFO | Corporate controller Plant controller Project Manager Plant Manager Quality Director
| 4.2 | Commercial Review (*) | [9 empty] | 2. Key Account Manager / Production Supervisor | 2.- BU Director / Production Manager | 2.- Project Manager / Plant Manager / Supply Chain Manager |  | Plant Manager Project Manager Plant Finance Manager Plant controller Corporate controller BU Director Purchasing Director
| 4.3 | Profitability Review (*) | [9 empty] | Project Manager | Plant controller | 3.- Plant Manager |  | Plant Manager Plant Finance Manager Corporate Controller BU Director Purchasing Director
| PHASE VALIDATION RESULT |  |  | PHASE LEAD
| Release Status: |  | Not started | Project Manager
Released by:
Release Date:

## 0. Items + RASIC
APQP Gate Release Checklist (APQP GRC) | [6 empty] | GATES RASIC CHART RESPONSIBLE ACCOUNTABLE SUPPORTING INFORMED CONSULTED |  |  |  |  | Open | OK | Automotive | TBD | TBD
[12 empty] | Conditionally closed | Cond. OK | Non-Automotive | PREMO Mediterranée | Da Nang
[13 empty] | N/A |  | PREMO Wuhu | Málaga
|  |  |  | Project Manager : | Project Name: | [10 empty] | Tangier
|  |  |  | PREMO P/N: | Part Description: | [10 empty] | Wuhu
|  |  |  | Customer P/N: | Customer Name:
|  |  |  | Samples Center: | Category:
|  |  |  | Manuf. Center: | Last Rev. Date:
1 | FEASIBILITY FOR OPPORTUNITIES - PHASE LEAD: BU DIRECTOR |  |  |  |  | Action item/Deliverable | Responsible | Accountable | Supporting | Informed | Consulted
Feasibility for Opportunities | 1.1 | CIR (Customer Input Requirements) |  |  |  | CIR Form (Technical/Commercial) | Key Account Manager | BU Director | Field Application Engineer | R&D Director / Corporate Quality Director | Category Design Leader
| 1.2 | Technical Feasibility |  |  |  | Technical Feasibility Analysis | Field Application Engineer | Key Account Manager | Product design engineer / Corporate controller | BU Director | Category Design Leader
| 1.3 | Project Committee Acceptance |  |  |  | 1.- Project Cttee Acceptance Submission 2.- Gate 1 Release Team definition and design/samples/manuf center definition inside PCA submission | 1.- Key Account Manager 2.- RD Director, Purchasing Director, Quality Director, Plant Manager, Operations Director | BU Director | Field Application Engineer | CFO / Sr. Management Team / Project Manager | CEO
| 1.4 | Previous DFMEA and Lessons Learnt |  |  |  | DFMEA and Lessons Learn up to date of the product family | Field Application Engineer | R&D Manager | Category Design Leader | Corporate Quality Director | Project Quality Engineer
| 1.5 | Technical definition |  |  |  |  | Product design engineer | Field Application Engineer | Process design engineer | R&D Director / Key Account Manager / Purchasing Officer / Project Quality Engineer | Category Design Leader
| 1.6 | PDCC completion |  |  |  | PDCC | PDCC team defined inside PDCC | Key Account Manager | Field Application Engineer | Corporate Controller / BU Director | Corporate Controller
| 1.7 | Samples WI |  |  |  | Samples WI (A) | Product design Engineer | R&D Manager | Process design Engineer | Field Application Engineer | Prototype Engineer
| 1.8 | Sample Production |  |  |  | 1. Sample Production Plan 2. SIR | 1.- Product design engineer 2.- Prototype Engineer | 1.- Field Application Engineer 2.- Product design engineer | Process design Engineer | Field Application Engineer | R&D Manager
| 1.9 | Customer Feedback |  |  |  | Customer feedback: Email, report summary | Key Account Manager | BU Director | Category Design Leader / Field Application Engineer | R&D Manager | Product design engineer
| 1.10 | Feasibility bundle (*) |  |  |  | Close Feasibility Bundle (project plan inside) | Project Manager | Key Account Manager | R&D Manager | BU Director / Plant Manager | R&D Director / Plant Manager
| 1.11 | Customer Agreement - LON (*) |  |  |  | 1.- RFQ Cttee Submission 2.- LON | Key Account Manager | BU Director | Project Manager | Sr. Management Team / Project Manager | Corporate Controller
| PHASE VALIDATION RESULT |  |  | PHASE LEAD
| Release Status: |  | Not started | BU Director
Released by:
Release Date:
2 | DESIGN VALIDATION - PHASE LEAD: CORP. RD DIRECTOR |  |  |  |  | Action item/Deliverable | Responsible | Accountable | Supporting | Informed | Consulted
Design Validation | 2.1 | Team Definition |  |  |  | Gate Release Team defined in GRC Form and in PDCC for all the gates (adding 2, 3 and 4) | Project Manager | Plant Manager | R&D Manager / QA Manager / Engineering Manager / Purchasing Manager / Production Manager/ Maintenance Manager / Supply Chain Manager | Sr. Management Team / Plant Management Team | Operations Director / R&D Director / QA Director / Purchasing Director
| 2.2 | Project Master Plan |  |  |  | PMP (Project Master Plan): 1. DV 2. PV 3. QTP 4. Supplier validation 5. Customer milestones vs Premo milestones | 1. Product design Engineer 2. Industrial Engineer 3. Project Quality Engineer 4. Purchasing Officer | Project Manager | 1.- Field Application Engineer 2.- Process design Engineer 3.- Laboratory Engineer 4.- Supplier Quality Engineer | R&D Director / BU Director / QA Director / Purchasing Director / Plant Manager / Key Account Manager | 1. R&D Manager 2. Engineering Manager 3. QA Manager 4. Purchasing Manager 5.- Key Account Manager
| 2.3 | Launch the investment |  |  |  | 1.- CAPEX Cttee Submission 2.- Investment system release | 1.- Project Manager 2.- Corporate controller | 1.- RD Director 2.- Project Manager | Quality Director / Purchasing Director / R&D Director | Purchasing Manager / Quality Manager / Plant Finance Manager / Plant Manager | CEO / CFO
| 2.4 | Project Kick off |  |  |  | Email or MoM | Project Manager | Plant Manager | R&D Manager / QA Manager / Engineering Manager / Purchasing Manager / Production Manager/ Maintenance Manager / Supply Chain Manager | Key Account Manager | BU Director / Operations Director
| 2.5 | Design Concept Review |  |  |  | 1.- Design Concept 2.- BOM (inside PDCC) 3.- Process Flowchart | 1 &2 .- Product design engineer 3.- Process design engineer | R&D Manager | 1 &2.- Process design engineer 3.- Industrial engineer | Project Manager / Purchasing Manager / R&D Director | Category Design Leader
| 2.6 | DFMEA and Preliminary PFMEA |  |  |  | 1.- DFMEA 2.- PFMEA | 1. Product design Engineer 2. Process design Engineer | Project Quality Engineer | Coporate QMS / Field Application Engineer | Engineering Manager/ Production Manager/ Plant Quality Manager / Project Manager | Corporate Quality Engineer / R&D Manager / Category Deisgn Leader / Engineering Manager
| 2.7 | Product & Process Technical Definition: |  |  |  | 1. Product Datasheet and Raw material specifications 2. Process Specifications | 1.- Product design engineer 2.- Process design Engineer | R&D Manager | Category Design Leader | KAM/ Engineering Manager / Project Manager / R&D Director / Corporate QMS | R&D Director
| 2.8 | Preliminary Control Plan |  |  |  | Control Plan | Project Quality Engineer | Corporate Quality Engineer | Process design engineer / Industrial engineer | Plant Quality Manager / Production Manager / Engineering Manager / R&D Manager | R&D Manager / Engineering Manager
| 2.9 | Preliminary Work Instruction |  |  |  | Samples WI (B) | Process Design Engineer | R&D Manager | Industrial Engineer / Manufacturing Engineer | Prototype Engineer | Prototype Engineer
| 2.10 | Qualification Test Plan (QTP) |  |  |  | Qualification Test Plan | Project Quality | QA Manager | Product design Engineer / Category Design Leader | Project Manager Lab Engineer | Customer / Project Manager
| 2.11 | DV Bundle (*) |  |  |  | Close DV Bundle: 1. Raw material inspection report (all sources) 2. Process DOE results (all sources - fix parameters) 3. Limit tolerance check (max, nom, min, for all sources) 4. QTP report (all sources - fix parameters) | 1. Lab. Engineer / IQC inspector 2. Prototype Engineer 3. Process Designer 4. Lab. Engineer | 1. Project Quality Engineer 2. Process Design Engineer 3. R&D Manager 4. Project Quality Engineer | Corporate QMS / Corporate Quality Engineer / Category Design Leader | Project Manager Key Account Manager | R&D Director / QA Director
| 2.12 | Product datasheet and process specifications |  |  |  | 1.- Product datasheet and Raw material specifications 2.- BOM and Packaging Agreement 3.- Process specifications | 1 & 2.- Product design Engineer 3.- Process design Engineer | R&D Manager | Corporate QMS | Project Manager | R&D Director / QA Director
| 2.13 | PFMEA |  |  |  | PFMEA | Process Design Engineer | Project Quality Engineer | Industrial Engineer / Manufacturing Engineer | Engineering Manager/ Quailty Manager/ Production Manager / R&D Manager / Project Manager | Corporate Quality Engineer / R&D Manager / Category Deisgn Leader / Engineering Manager
| 2.14 | PDCC & Profitability reviewed |  |  |  | PDCC | PDCC team defined inside PDCC | Project Manager | R&D Director / Purchasing Director / Plant Manager | BU Director | Corporate controller
| 2.15 | SOCO for Raw Material (*) |  |  |  | SOCO for Raw Material | Purchasing Officer | Purchasing Manager | Product design Engineer / Supplier Quality Engineer / Corporate controller | Project Quality Engineer / Project Manager | Purchasing Director
| 2.16 | SOCO for Machine & Equipment (internal - no sourcing decision to supplier) (*) |  |  |  | SOCO for Machine & Equipment (internal only - no sourcing decision to supplier) | Industrial Engineer | Engineering Manager | Process design Engineer / Corporate controller | Project Quality Engineer / Project Manager | Operations Director / Plant Manager
| PHASE VALIDATION RESULT |  |  | PHASE LEAD
| Release Status: |  | Not started | Corp. RD Director
Released by:
Release Date:
3 | INDUSTRIALIZATION - PHASE LEAD: PLANT MANAGER |  |  |  |  | Action item/Deliverable | Responsible | Accountable | Supporting | Informed | Consulted
Industrialization | 3.1 | Launch the investment |  |  |  | 1.- CAPEX Ctte Submission 2.- Investment system release | 1.- Project Manager 2.- Corporate controller | 1.- Plant Manager 2.- Project Manager | Quality Director / Purchasing Director / Operations Director | Purchasing Manager / Quality Manager / Engineering Manager / Plant Finance Manager | CEO / CFO
| 3.2 | Definitve Production Layout |  |  |  | Full Operating Layout | Industrial Engineer | Engineering Manager | Facilities Manager | Facilities Manager / Production Manager / HSE Supervisor | Plant Manager
| 3.3 | Equipment installation |  |  |  | 1.- FAT Report 2.- Installation checklist | 1.- Industrial Engineer 2.- Maintenance Engineer | Engineering Manager | Facilities Manager/ Maintenance Manager / Supply Chain Manager | Facilities Manager / Production Manager / HSE Supervisor | Plant Manager
| 3.4 | Raw Material approved (PPAP) & Capacity Verification (Run@Rate) |  |  |  | RM PPAP approved (all suppliers) | Project Quality Engineer | Purchasing Officer | Supply Chain Manager / Engineering Manager / R&D Manager | Supply Chain Manager / QA Manager / Corporate Quality Systems / Project Manager / Purchasing Manager | Supplier Quality Engineer
| 3.5 | Material Reception & Delivery |  |  |  | 1. WI for Packaging (FGs in pallets) / shipment preparation (Family) 2. WI for Storage (Family) 3. WI for Incoming Inspection 4. Tools for incoming inspection | 1. Warehouse Supervisor 2. Warehouse Supervisor 3. Project Quality Inspector 4. Industrial Engineer | 1. Supply Chain Manager 2. Supply Chain Manager 3 &4. Project Quality Engineer | Purchasing Officer / Product design Engineer | Production Manager Supply Chain Manager Engineering Manager QA Manager | 1, 2 & 4.- Quality Control Engineer 3. SQE / IQC inspector
| 3.6 | IQ (Installation Qualification) |  |  |  | IQ Bundle | Industrial Engineer | Engineering Manager | Process Design Engineer / Maintenance Engineer | Production Manager QA Manager | Plant Manager / Finance Manager
| 3.7 | OQ (Operation Qualification) |  |  |  | OQ Bundle: 1. Setup Work Instructions & records 2. Spare part list 3. Preventive Maintenance Plan and WI 4. Machine R@R | 1, 2, 3. Maintenance Engineer 4. Industrial Engineer | Engineering Manager | Process Design Engineer | R&D Manager Project Quality Engineer QA Manager Production Manager | Plant Manager / Maintenance Manager
| 3.8 | PQ (Performance Qualification) |  |  |  | PQ Bundle: 1.- Machine setup and DOE 2. MSA (all stations GO/NG, fixed process parameters) 3. Gage R&R (all manufacturing processes and test processes with numerical result, fixed process parameters) | 1. Industrial Engineer 2, 3. Project Quality Engineer | Engineering Manager | Manufacturing Engineer / Quality Control Engineer | Production Manager QA Manager Maintenance Manager | Plant Manager / QA Manager
| 3.9 | Definitive Process Documentation |  |  |  | 1. PFMEA 2. Control Plan | 1. Industrial Engineer 2. Project Quality Engineer | 1. Project Quality Engineer 2. Quality Control Engineer | Corporate Quality Systems / Process design Engineer / Manufacturing Engineer / Maintenance Engineer | Production Manager QA Manager Engineering Manager Maintenance Manager | QA Manager
| 3.10 | Wis and Training |  |  |  | 1. Manufacturing Work Instructions 2. Training Plan and Training Matrix (Production / Quality) | 1. Manufacturing Engineer 2. Production Supervisor / Quality Control Engineer | 1. Production Manager 2. Production Manager / QA Manager | 1. Industrial Engineer 2. HSE Supervisor / HR Supervisor | QA Manager / Engineering Manager / HR Manager | 1. Production Supervisor 2. Quality Supervisor
| 3.11 | Line Release Audit - Including New Equipment, Tooling, and Test Equipment Release (*) |  |  |  | Line Release Report: 1. Run @ Rate 2. Process Audit (VDA 6.3) 3. Closing Meeting (Line Release Report should be available) 4. Action plan approval and launch (2 weeks max timing) | 1. Industrial Engineer / Manufacturing Engineer 2. Project Quality Engineer 3. QA Manager 4. Engineering Manager | 1. Engineering Manager / Production Manager 2. QA Manager 3 & 4. Project Manager | Corporate QMS / Quality System Engineer | Supply Chain Manager Production Manager Maintenance Manager Corporate Controller Plant Finance Manager Plant Manager Quality Director BU Director | Plant Manager / Quality Director
| 3.12 | QTP batch manufacturing with full conditions |  |  |  | 1. QTP batch manufacturing 2. QTP test 3. QTP Report | 1. Industrial Engineer 2 & 3. Lab. Engineer | Project Quality Engineer | QA Manager Corporate Quality Systems Project Manager | Key Account Manager R&D Manager & Director Maintenance Manager Plant Manager QA Director Project Manager | Plant Manager / Quality Director
| 3.13 | FMEA and Control Plan final review and release |  |  |  | 1. PFMEA 2. Control Plan | 1. Industrial Engineer 2. Project Quality Engineer | 1. Project Quality Engineer 2. Process Quality Engineer | Corporate Quality Systems / Process Design Engineer / Manufacturing Engineer / Maintenance Engineer | Production Manager QA Manager Engineering Manager Maintenance Manager | QA Manager
| 3.14 | PDCC & Profitability reviewed - Fix route and scrap |  |  |  | PDCC | PDCC team defined inside PDCC | Project Manager | R&D Director / Purchasing Director / Plant Manager | BU Director | Corporate controller
| 3.15 | PPAP Approval (PSW Signed) - Received & Reviewed (*) |  |  |  | PPAP | Project Quality Engineer | QA Manager | Engineering Manager / Corporate Quality Systems / Project Manager | Key Account Manager Engineering Manager Production Manager Quality Manager Supply Chain Manager Maintenance Manager Quality Director | Plant Manager / Quality Director
| PHASE VALIDATION RESULT |  |  | PHASE LEAD
| Release Status: |  | Not started | Plant Manager
Released by:
Release Date:
4 | SOP + 6 MONTHS - PHASE LEAD: PROJECT MANAGER |  |  |  |  | Action item/Deliverable | Responsible | Accountable | Supporting | Informed | Consulted
SOP + 6 Months | 4.1 | Quality Review (*) |  |  |  | SOP Review format (Int/Ext Claims, Safe launch/Quality walls, Achievement vs LON, Deliveries vs orders, Actual profitability vs PDCC) | 1.- Quality Control Engineer / Customer Quality Engineer | 1.- QA Manager | 1.- Quality Director / Plant Manager | Corporate controller Plant controller Project Manager Plant Manager Quality Director | CEO/CFO
| 4.2 | Commercial Review (*) |  |  |  |  | 2. Key Account Manager / Production Supervisor | 2.- BU Director / Production Manager | 2.- Project Manager / Plant Manager / Supply Chain Manager | Plant Manager Project Manager Plant Finance Manager Plant controller Corporate controller BU Director Purchasing Director
| 4.3 | Profitability Review (*) |  |  |  |  | Project Manager | Plant controller | 3.- Plant Manager | Plant Manager Plant Finance Manager Corporate Controller BU Director Purchasing Director
| PHASE VALIDATION RESULT |  |  | PHASE LEAD
| Release Status: |  | Not started | Project Manager
Released by:
Release Date:

## 1. Feasibility
APQP Gate Release Checklist (APQP GRC) FEASIBILITY FOR OPPORTUNITIES - PHASE LEAD: BU DIRECTOR | [14 empty] | Pending | Open | OK | Automotive | TBD | TBD
[15 empty] | WIP | Conditionally closed | Cond. OK | Non-Automotive | PREMO Mediterranée | Da Nang | Open
[15 empty] | Done |  | N/A |  | PREMO Wuhu | Málaga | Closed
[7 empty] | Project Manager : | Name Surname |  | Project Name: |  |  |  |  | Reviewed |  |  |  |  | Tangier
[7 empty] | PREMO P/N: | X-12345-678 |  | Part Description: |  |  |  |  | Approved |  |  |  |  | Wuhu
[7 empty] | Customer P/N: | RT23423AA |  | º |  | Name of the customer |  |  | Rejected
[7 empty] | Samples Center: |  |  | Category:
[7 empty] | Manuf. Center: |  |  | Last Rev. Date:
1 | # | Gate | [5 empty] | Action item/Deliverable | Status | Planned Date | Closed Date | Link to deliverable | Remarks / Gaps | Criteria for acceptance
Feasibility for Opportunities | 1.1 | CIR (Customer Input Requirements) | [5 empty] | CIR Form (Technical/Commercial) | Pending |  |  |  |  | 1.- All mandatory fields filled in 2.- Reviewed by BU Director
| 1.2 | Technical Feasibility | [5 empty] | Technical Feasibility Analysis | Pending |  |  |  |  | 1.- Technical feasibility analysis result is determined (OK/NG): product/process requirements cross check and estimated margin (quick costing done) 2.- Reviewed by CDL
| 1.3 | Project Committe Acceptance | [5 empty] | 1.- Project Cttee Acceptance Submission 2.- Gate 1 Release Team definition and design/samples/manuf center definition inside PCA submission | Pending |  |  |  |  | 1.- Technical feasibility analysis result must be OK 2.- All mandatory fields filled in 3.- Reviewed by CDL
| 1.4 | Previous DFMEA and Lessons Learnt | [5 empty] | DFMEA and Lessons Learn up to date of the product family | Pending |  |  |  |  | 1.- Family FMEA is reviewed by FAE
| 1.5 | Technical definition | [5 empty] | 1. Design Concept 2. BOM & Process Flowchart (inside PDCC) 3. Preliminary Datasheet | Pending |  |  |  |  | 1.- Design Concept: all mandatory fields fileld in (BOM and Flowchart) 2.- BOM & Process Flowchart in PDCC matching with Design Concept 3.- Preliminary Datasheet is complete and reviewed by RD Manager/Supervisor/CDL
| 1.6 | PDCC completion | [5 empty] | PDCC | Pending |  |  |  |  | 1.- All mandatory fields filled in 2.- Reviewed by Functional Managers (Purchasing, RD) 3.- Reviewed by Corporate controlling for consistency
| 1.7 | Samples WI | [5 empty] | Samples WI (A) | Pending |  |  |  |  | 1.- All materials of BOM and process steps inside PDCC/Design Concept are included. Visuals may be provided with 3D drawing snapshots at this stage. 2.- Quality criteria for each step and technology to be used is defined. No need to specify process parameters, only record them in SIR later. 3.- Reviewed by RD Supervisor/Manager
| 1.8 | Sample Production | [5 empty] | 1. Sample Production Plan 2. SIR | Pending |  |  |  |  | 1.- Sample Production Plan: all mandatory fields are filled in and reviewed by FAE/RD Manager 2.- SIR: all mandatory fields are filled in (including 3rd and extreme test/disassembly) and reviewed by Product design engineer
| 1.9 | Customer Feedback | [5 empty] | Customer feedback: Email, report summary | Pending |  |  |  |  | Evidence is available
| 1.10 | Feasibility bundle (*) | [5 empty] | Close Feasibility Bundle (project plan inside) | Pending |  |  |  |  | 1.- Close Feasibility Bundle result is determined (OK/NG) based on timeline, pricing and technical feasibility by customer. Includes Logistics Protocol. 2.- Close Feasibility Bundle is reviewed by senior management team (RD Director/QA Director/Plant Manager/Purchasing Director)
| 1.11 | Customer Agreement - LON (*) | [5 empty] | 1.- RFQ Cttee Submission 2.- LON | Pending |  |  |  |  | 1.- Close Feasibility Bundle result is OK from customer and internal review. 2.- RFQ Cttee Submission conditions match with LON conditions 3.- LON is reviewed by Corporate Controlling 4.- LON is signed by CFO/CEO
| PHASE VALIDATION RESULT |  |  |  | PHASE LEAD
| Release Status: |  | Not started |  | BU Director
Released by:
Release Date:
ACTIONS TO DO IN CASE OF CONDITIONAL APPROVAL
| # | RESPONSIBLE |  | DUE DATE | CLOSE DATE | STATUS | DESCRIPTION
1
2
3
4
5
6
7
8
9
10

## 2.Design Validation
APQP Gate Release Checklist (APQP GRC) DESIGN VALIDATION - PHASE LEAD: CORP RD DIRECTOR | [13 empty] | Open | OK | Automotive | TBD | TBD
[14 empty] | Conditionally closed | Cond. OK | Non-Automotive | PREMO Mediterranée | Da Nang
[15 empty] | N/A |  | PREMO Wuhu | Málaga
[6 empty] | Project Manager : | Name Surname |  | Project Name: | [8 empty] | Tangier
[6 empty] | PREMO P/N: | X-12345-678 |  | Part Description: | [8 empty] | Wuhu
[6 empty] | Customer P/N: | RT23423AA |  | º |  | Name of the customer
[6 empty] | Samples Center: |  |  | Category:
[6 empty] | Manuf. Center: |  |  | Last Rev. Date:
2 | # | Gate |  |  |  |  | Action item/Deliverable | Status | Planned Date | Closed Date | Link to deliverable | Remarks / Gaps | Criteria for acceptance
Design Validation | 2.1 | Team Definition |  |  |  |  | Gate Release Team defined in GRC Form and in PDCC for all the gates (adding 2, 3 and 4) | Pending |  |  |  |  | 1.- Gate Release Team for all gates defined (adding 2, 3 and 4) 2.- Team definition coordinated with functions and communicated to responsibles and management
| 2.2 | Project Master Plan |  |  |  |  | PMP (Project Master Plan): 1. DV 2. PV 3. QTP 4. Supplier validation 5. Customer milestones vs Premo milestones | Pending |  |  |  |  | 1.- All plans are available 2.- Customer milestones are achievable 3.- Plans are reviewed by Functional managers
| 2.3 | Launch the investment |  |  |  |  | 1.- CAPEX Cttee Submission 2.- Investment system release | Pending |  |  |  |  | 1.- CAPEX Cttee Submission: all mandatory data is filled in (project introduction, technical presentation, investment list, economical analysis) and is presented in Monthly CAPEX meeting to Senior Mgmt 2.- Investment system release: CAPEX Cttee Submission is approved by CEO and CFO and CO order released for the approved amount
| 2.4 | Project Kick off |  |  |  |  | Email or MoM | Pending |  |  |  |  | MoM is available
| 2.5 | Design Concept Review |  |  |  |  | 1.- Design Concept 2.- BOM (inside PDCC) 3.- Process Flowchart | Pending |  |  |  |  | 1.- Design Concept: all mandatory fields fileld in (BOM and Flowchart) 2.- BOM & Process Flowchart in PDCC matching with Design Concept 3.- Process Flowchart defines all steps of the process (manufacturing and control)
| 2.6 | DFMEA and Preliminary PFMEA |  |  |  |  | 1.- DFMEA 2.- PFMEA | Pending |  |  |  |  | 1.The DFMEA includes all customer requirements, and the PFMEA includes all process steps and product characteristics, integrating poka‑yoke concepts to prevent potential errors at the source. 2.Actions are implemented based on the assigned Action Priority (AP): – For AP High, the team must define and implement actions to improve prevention and/or detection controls, prioritizing poka‑yoke solutions when feasible. – For AP Medium, the team should identify appropriate actions or formally justify why existing controls are adequate. – For AP Low, the team may consider additional improvements when beneficial. 3.Both FMEAs are reviewed by the Functional Manager and CDL, ensuring that all risk‑reduction measures, including applicable poka‑yoke mechanisms, are properly assessed and validated.
| 2.7 | Product & Process Technical Definition: |  |  |  |  | 1. Product Datasheet and Raw material specifications 2. Process Specifications | Pending |  |  |  |  | 1.- Product Datasheet and Raw material specifications: all mandatory fields are filled in and document is reviewed by RD Manager 2.- Process Specifications: all process steps in flow chart are included and full requirements of process are defined (controls, manufacturing parameters, technology to be used, cycle time and others)
| 2.8 | Preliminary Control Plan |  |  |  |  | Control Plan | Pending |  |  |  |  | 1.- Control plan: all process steps, product and process characteristics are covered 2.- Control plan is reviewed by Corporate Quality Engineer, Engineering Manager and RD Manager
| 2.9 | Preliminary Work Instruction |  |  |  |  | Samples WI (B) | Pending |  |  |  |  | 1.- All materials of BOM and process steps inside PDCC/Design Concept are included. Visuals are provided with pictures of real parts. 2.- Quality criteria and process parameters for each step and technology to be used is defined 3.- Reviewed by RD Supervisor/Manager
| 2.10 | Qualification Test Plan (QTP) |  |  |  |  | Qualification Test Plan | Pending |  |  |  |  | 1.- All tests compliant to AECQ-200 and specific customer requirements are considered 2.- Timeline with quantities needed and planned dates for tests is available and can match planned schedule for the phase 3.- QTP plan is reviewed by Project Manager and QA Manager
| 2.11 | DV Bundle (*) |  |  |  |  | Close DV Bundle: 1. Raw material inspection report (all sources) 2. Process DOE results (all sources - fix parameters) 3. Limit tolerance check (max, nom, min, for all sources) 4. QTP report (all sources - fix parameters) | Pending |  |  |  |  | 1.- All mandatory fields are filled in 2.- Manufacturability assessment result is pass (process DOE) 3.- Limit tolerance is fixed for each RM 4.- QTP report result is passed for all tolerances of at least one source for each RM
| 2.12 | Product datasheet and process specifications |  |  |  |  | 1.- Product datasheet and Raw material specifications 2.- BOM and Packaging Agreement 3.- Process specifications | Pending |  |  |  |  | 1.- Product Datasheet and Raw material specifications: all mandatory fields are filled in and document is reviewed by RD Manager. Parameters should match with validated QTP results. 2.- BOM updated according with QTP results and Packaging agreed with customer 3.- Process Specifications: all process steps in flow chart are included and full requirements of process are defined (controls, manufacturing parameters, technology to be used, cycle time and others). Parameters should match with validated QTP results.
| 2.13 | PFMEA |  |  |  |  | PFMEA | Pending |  |  |  |  | 1.- PFMEA is including all process steps and product characteristics 2.- There is always action when RPN is higher than defined limit (100) 3.- PFMEA is reviewed by Functional Manager and CDL
| 2.14 | PDCC & Profitability reviewed |  |  |  |  | PDCC | Pending |  |  |  |  | 1.- All mandatory fields filled in 2.- Reviewed by Functional Managers (Purchasing, RD) 3.- Reviewed by Corporate controlling for consistency 4.- CM matches RFQ PDCC and in case it doesn't, then there is an action plan approved by management
| 2.15 | SOCO for Raw Material (*) |  |  |  |  | SOCO for Raw Material | Pending |  |  |  |  | 1. Supplier is sourceable (already approved, no NBH or potential supplier audit passed) 2. Supplier Technical Feasibility Gate to be closed before nomination 3. Samples delivered and test passed 4. RM APQP open in VEGA for all new parts 5. GTC and Suppplier Quality Agreement signed by all suppliers 6.- At least 3 quotes are presented and the quotation nominated is matching the target cost in PDCC 7.- Cost breakdown is available for presented quotes 8.- Detailed timeline is available and complies with project timing requirements
| 2.16 | SOCO for Machine & Equipment (internal - no sourcing decision to supplier) (*) |  |  |  |  | SOCO for Machine & Equipment (internal only - no sourcing decision to supplier) | Pending |  |  |  |  | 1. Supplier Technical Feasibility vs Process specification is passed 2.- At least 3 quotes are presented and the quotation nominated is matching the target CAPEX in PDCC 3.- Cost breakdown is available for presented quotes 4.- Detailed timeline is available and complies with project timing requirements
| PHASE VALIDATION RESULT |  |  |  | PHASE LEAD
| Release Status: |  | Not started |  | RD Director
Released by:
Release Date:
ACTIONS TO DO IN CASE OF CONDITIONAL APPROVAL
| # | RESPONSIBLE |  | DUE DATE | CLOSE DATE | STATUS | DESCRIPTION
1
2
3
4
5
6
7
8
9
10

## 3. Industrialization
APQP Gate Release Checklist (APQP GRC) INDUSTRIALIZATION - PHASE LEAD: PLANT MANAGER | [13 empty] | Open | OK | Automotive | TBD | TBD
[14 empty] | Conditionally closed | Cond. OK | Non-Automotive | PREMO Mediterranée | Da Nang
[15 empty] | N/A |  | PREMO Wuhu | Málaga
[6 empty] | Project Manager : | Name Surname |  | Project Name: | [8 empty] | Tangier
[6 empty] | PREMO P/N: | X-12345-678 |  | Part Description: | [8 empty] | Wuhu
[6 empty] | Customer P/N: | RT23423AA |  | º |  | Name of the customer
[6 empty] | Samples Center: |  |  | Category:
[6 empty] | Manuf. Center: |  |  | Last Rev. Date:
3 | # | Gate |  |  |  |  | Action item/Deliverable | Status | Planned Date | Closed Date | Link to deliverable | Remarks / Gaps | Criteria for acceptance
Industrialization | 3.1 | Launch the investment |  |  |  |  | 1.- CAPEX Ctte Submission 2.- Investment system release | Pending |  |  |  |  | 1.- CAPEX Cttee Submission: all mandatory data is filled in (project introduction, technical presentation, investment list, economical analysis) and is presented in Monthly CAPEX meeting to Senior Mgmt 2.- Investment system release: CAPEX Cttee Submission is approved by CEO and CFO and CO order released for the approved amount
| 3.2 | Definitve Production Layout |  |  |  |  | Full Operating Layout | Pending |  |  |  |  | 1.- All machines, equipments and accessories of the line are depicted in the production layout and consistent with the process flow chart. 2.- All material movements are depicted in the layout and consistent with the process flow chart. 3.- All direct employees operating the line are depicted in the layout and consistent with the process flow chart. 4.- Full Operating Layout is reviewed by Plant Manager
| 3.3 | Equipment installation |  |  |  |  | 1.- FAT Report 2.- Installation checklist | Pending |  |  |  |  | 1.- FAT Report: all mandatory fields are filled in (machinery construction and assembly is fully completed and all functions implemented) and reviewed by Engineering Manager 2.- Installation checklist: all mandatory fields are filled in (neumatics, electricity, oil and other installations completed successfully) and reviewed by Facility/Engineering Manager
| 3.4 | Raw Material approved (PPAP) & Capacity Verification (Run@Rate) |  |  |  |  | RM PPAP approved (all suppliers) | Pending |  |  |  |  | 1.- Run and Rate's score is passed vs PDCC requested capacity 2.- QTP in DV passed for the material (DV Bundle) 3.- Control plan from supplier is audited and approved by Premo 4.- Supplier datasheet matching with Premo RM Specification and reviewed and approved by Premo
| 3.5 | Material Reception & Delivery |  |  |  |  | 1. WI for Packaging (FGs in pallets) / shipment preparation (Family) 2. WI for Storage (Family) 3. WI for Incoming Inspection 4. Tools for incoming inspection | Pending |  |  |  |  | 1.- WI for Packaging: Family WI is updated and reviewed by Supply Chain Manager 2.- WI for Storage: Family WI is updated and reviewed by Supply Chain Manager 3.- WI for Incoming Inspection: all special characteristics in RM Specification are mentioned and controlled with proper equipment and reviewed by QA Manager
| 3.6 | IQ (Installation Qualification) |  |  |  |  | IQ Bundle | Pending |  |  |  |  | 1.- Pre-installation verification: overall inspection without damages/abnormalities, no missing components 2.- Installation verification: power on/off, basic setup check, components/equipments status 3.- Functional verification: all features present and working, worst case check
| 3.7 | OQ (Operation Qualification) |  |  |  |  | OQ Bundle: 1. Setup Work Instructions & records 2. Spare part list 3. Preventive Maintenance Plan and WI 4. Machine R@R | Pending |  |  |  |  | 1.- Setup Work Instructions & records: all steps to setup the machine are mentioned and well documented and reviewed by Maintenance Manager 2.- Spare part list: all needed spare parts are listed and reviewed by Maintenance Manager 3.- Preventive Maintenance Plan and WI: all items that are needed are mentioned and reviewed with Maintenance Manager 4.- Machine R@R: result of OEE pass versus defined PDCC target and reviewed by Engineering Manager
| 3.8 | PQ (Performance Qualification) |  |  |  |  | PQ Bundle: 1.- Machine setup and DOE 2. MSA (all stations GO/NG, fixed process parameters) 3. Gage R&R (all manufacturing processes and test processes with numerical result, fixed process parameters) | Pending |  |  |  |  | 1.- MSA (all stations GO/NG, fixed process parameters): result is pass. 2.- Gage R&R (all manufacturing processes and test processes with numerical result, fixed process parameters): result is pass.
| 3.9 | Definitive Process Documentation |  |  |  |  | 1. PFMEA 2. Control Plan | Pending |  |  |  |  | 1.- PFMEA is including all process steps and product characteristics 2.- There is always action when RPN is higher than defined limit (100) 3.- PFMEA is reviewed by Functional Manager and CDL 4.- Control plan: all process steps, product and process characteristics are covered 5.- Control plan is reviewed by Quality Manager, Engineering Manager and Production Manager
| 3.10 | Wis and Training |  |  |  |  | 1. Manufacturing Work Instructions 2. Training Plan and Training Matrix (Production / Quality) | Pending |  |  |  |  | 1.- All materials of BOM and process steps inside PDCC/Design Concept are included. Visuals are provided with pictures of real parts. 2.- Quality criteria and process parameters for each step and technology to be used is defined. Visuals of NG and Good parts are clearly defined with pictures of real parts. 3.- The set of toolings and parameters to operate each station is clearly defined and aligned with control plan, stablishing a 6S standard for compliance 4.- The sequence of operation in each station of the process is defined in detail and with supportive pictures to let operator understand (specially in manual stations) 5.- Reviewed by Production Manager
| 3.11 | Line Release Audit - Including New Equipment, Tooling, and Test Equipment Release (*) |  |  |  |  | Line Release Report: 1. Run @ Rate 2. Process Audit (VDA 6.3) 3. Closing Meeting (Line Release Report should be available) 4. Action plan approval and launch (2 weeks max timing) | Pending |  |  |  |  | 1.- Run & Rate result is pass 2.- Process Audit result is pass 3.- Line Release Report is signed by Plant Manager and agreed by all Functional managers in the plant
| 3.12 | QTP batch manufacturing with full conditions |  |  |  |  | 1. QTP batch manufacturing 2. QTP test 3. QTP Report | Pending |  |  |  |  | 1.- QTP Report result is pass 2.- QTP Report is containing all test results from the tests highlighted in QTP plan 3.- QTP Report contains pictures and measurements of the real parts for each test and the parts are physically available for inspection if requested
| 3.13 | FMEA and Control Plan final review and release |  |  |  |  | 1. PFMEA 2. Control Plan | Pending |  |  |  |  | 1.- PFMEA is including all process steps and product characteristics 2.- There is always action when RPN is higher than defined limit (100) 3.- PFMEA is reviewed by Functional Manager and CDL 4.- Control plan: all process steps, product and process characteristics are covered 5.- Control plan is reviewed by Quality Manager, Engineering Manager and Production Manager
| 3.14 | PDCC & Profitability reviewed - Fix route and scrap |  |  |  |  | PDCC | Pending |  |  |  |  | 1.- All mandatory fields filled in 2.- Reviewed by Functional Managers (Purchasing, RD) 3.- Reviewed by Corporate controlling for consistency 4.- CM matches RFQ PDCC and in case it doesn't, then there is an action plan approved by management
| 3.15 | PPAP Approval (PSW Signed) - Received & Reviewed (*) |  |  |  |  | PPAP | Pending |  |  |  |  | 1.- PPAP is approved by customer 2.- PPAP is reviewed by all Functional Managers 3.- PPAP is signed by Plant Manager/QA Director
| PHASE VALIDATION RESULT |  |  |  | PHASE LEAD
| Release Status: |  | Not started |  | Plant Manager
Released by:
Release Date:
ACTIONS TO DO IN CASE OF CONDITIONAL APPROVAL
| # | RESPONSIBLE |  | DUE DATE | CLOSE DATE | STATUS | DESCRIPTION
1
2
3
4
5
6
7
8
9
10

## 4. SOP+6M
APQP Gate Release Checklist (APQP GRC) SOP + 6 MONTHS - PHASE LEAD: PROJECT MANAGER | [14 empty] | Open | OK | Automotive | TBD | TBD
[15 empty] | Conditionally closed | Cond. OK | Non-Automotive | PREMO Mediterranée | Da Nang
[16 empty] | N/A |  | PREMO Wuhu | Málaga
[5 empty] | Project Manager : | Name Surname |  | Project Name: | [10 empty] | Tangier
[5 empty] | PREMO P/N: | X-12345-678 |  | Part Description: | [10 empty] | Wuhu
[5 empty] | Customer P/N: | RT23423AA |  | º | Name of the customer
[5 empty] | Samples Center: |  |  | Category:
[5 empty] | Manuf. Center: |  |  | Last Rev. Date:
4 | # | Gate | [5 empty] | Action item/Deliverable | Status | Planned Date | Closed Date | Link to deliverable | Remarks / Gaps | Criteria for acceptance
SOP + 6 Months | 4.1 | Quality Review (*) | [5 empty] | SOP Review format (Int/Ext Claims, Safe launch/Quality walls, Achievement vs LON, Deliveries vs orders, Actual profitability vs PDCC) | Pending |  |  |  |  | 1.- No claims in 6 months after project start or in a period of 6 months from last claim received 2.- Achievement matches with LON and deliveries are done according to orders without delay 3.- CM in PDCC matches CM in RFQ PDCC
| 4.2 | Commercial Review (*) | [6 empty] | Pending
| 4.3 | Profitability Review (*) | [6 empty] | Pending
| PHASE VALIDATION RESULT |  |  |  | PHASE LEAD
| Release Status: |  | Not started |  | Project Manager
Released by:
Release Date:
ACTIONS TO DO IN CASE OF CONDITIONAL APPROVAL
| # | RESPONSIBLE |  | DUE DATE | CLOSE DATE | STATUS | DESCRIPTION
1
2
3
4
5
6
7
8
9
10

## Gate Release Team
Gate Release Team
QG1 | KAM | Open | OK | Automotive | TBD | TBD
| BU Director | Conditionally closed | Cond. OK | Non-Automotive | PREMO Mediterranée | Da Nang
| CDL |  | N/A |  | PREMO Wuhu | Málaga
| FAE |  |  |  |  | Tangier
| Product design Engineer |  |  |  |  | Wuhu
Process design Engineer
Prototype Engineer
RD Manager
Project Quality Engineer
Purchasing Officer
Corporate controller
Project Manager
Plant Manager
Project Quality Inspector
Samples leader/operator
Project Manager
QG2 | Industrial Engineer
Engineering Manager
Quality Manager
Purchasing Manager
Maintenance Manager
Supply Chain Manager
Finance Manager
Corporate QMS
Manufacturing Engineer
Production Manager
Corporate Quality Engineer
Lab Engineer
IQC inspector
Supplier Quality Engineer
QG3 | Facilities Manager
Quality System Engineer
HSE supervisor
Quality Supervisor
Quality Control Engineer
Production Supervisor
Warehouse supervisor
Maintenance engineer
HR Supervisor
HR Manager
QG4 | Plant controller
Customer Quality Engineer

## Ed. Control
REVISION HISTORY
Rev. | Date | Modification | Made by | Checked by | Approved by
01 | 2024-07-04 | Initial version of the document | Yogeshkumar L. | J.Muñoz | J.M. Pichot
02 | 2024-08-14 | Requirements reviewed. Format update. Added Possible requirements and evidences column. Added Remarks/Gaps column. Name updated to APQP GRC | J.Muñoz | O.Gutiérrez | Yogeshkumar L.
03 | 2024-10-21 | General update of the checklist | J.Muñoz | O.Gutiérrez | Yogeshkumar L.
04 | 2024-11-25 | Added "Responsible" and "Evidence" columns. Note in the header updated. "Design No" updated to Spec edition". "Review date" moved below "Reviewed by". ST2 Item 5 abd ST4 item 12 description updated. | J.Muñoz | O.Gutiérrez | Yogeshkumar L.
05 | 2024-12-13 | "Responsibles" column updated | J.Muñoz | O.Gutiérrez | Yogeshkumar L.
06 | 2025-07-02 | General form review and update. Added "Released by, Date, Status, Gate validation Team" for each stage. Removed APQP Risk. Removed unused fields on header. Added/updated/removed items in DV/PV/PDPV stages. Added Category "Automotive/Non Automotive" | J.Muñoz | O.Gutiérrez | M. Yamada
07 | 2025-08-11 | Added RACI Matrix Changed sequence of gates and naming Changed gate items and deliverables Added new columns to assess validity of items General form review and update Added Quality Gate Lead Added Gate Release Team | A. García | A. García | A. García
08 | 2025-08-18 | Split file into different sheets for better visibility and formatting | Jose Lasierra | A. García | A. García
09 | 2026-04-29 | Added Conditional Approval in the project phase | J.Muñoz / O. Gutiérrez | D. Patel | A. García

## APQP GRC Non-Auto (PENDING)
(This column should be hidden)
|  |  | APQP Gate Release Checklist (APQP GRC) | [11 empty] | Open | OK | Automotive | TBD | TBD
[11 empty] | GL-00-002-F-001. Ver: 6.0 |  |  |  | Conditionally closed | Cond. OK | Non-Automotive | PREMO Mediterranée | Da Nang
|  | Note: All documentation of APQP at respective stage complete, Agreed & Released by Cross-Functional Team. | [12 empty] | Closed | NO OK |  | PREMO Vietnam | India
*PM must schedule phase review 15 working days with Quality Manager before PVC date and agenda for PVC to be fixed by PM before 3 working days of PVC date. | [15 empty] | N/A |  | PREMO Wuhu | Málaga
|  |  | Project Manager : |  |  | Project Name: | [12 empty] | Tangier
|  |  | PREMO P/N: |  |  | Part Description: | [12 empty] | Wuhu
|  |  | Customer P/N: |  |  | Customer Name:
|  |  | Samples Center: |  |  | Category: | Non-Automotive
|  |  | Manuf. Center: |  |  | Last Rev. Date:
1 | TEAM + FEASIBILITY (PLANNING) | [6 empty] | Evidence | Responsible | Applicable for No Auto | Status | Evidence (short link) | Remarks / Gaps | Defined Actions
PFA Feasibility | 1.1 | Team defined, stake holders from key functions/expertise available | [5 empty] | Project Information tab in Project Management > Project_information.xls | Project Manager | X
| 1.2 | Project Kick off done and information shared with all project team | [5 empty] | Project Management > [email or MoM] | Project Manager | X
| 1.3 | Project plan | [5 empty] | Project Management > Project_information.xls, Tab Timeplan | Project Manager | X
| 1.4 | Customer Input Requirements available and clear. | [5 empty] | Customer Spec, Email or any evidence of customer request | Sales | X
| 1.5 | Preliminary BOM available | [5 empty] | Raw Material tab in PDCC and BOM in SAP | R&D | X
| 1.6 | Preliminary PREMO Specification | [5 empty] | Premo specification "V0" for Feasibility | R&D | X
| 1.7 | Design Verification (Samples Inspection Report / SIR) (if applicable) | [5 empty] | Sample Inspection Report (SIR) for feasibility samples | Engineering | X
| 1.8 | Manufacturing Working Instruction (Samples Inspection Report / SIR) (if applicable) | [5 empty] | WI for Feasibility samples (if needed, not mandatory) | Engineering | X
| 1.9 | PDCC reviewed | [5 empty] | PDCC | Project Team (leaded by PM) | X
| 1.10 | Previous DFMEA & Lesson Learnt review | [5 empty] | If Lessons learnt applied, to add the Lessons Learnt ID from Database // For DFMEA review, add the reference of the Part Number and DFMEA Ed | Project Team | X
| 1.11 | Preliminary List of special product and process characteristics | [5 empty] | List of Special Characteristics (if required by customer) in Quality folder OR Characteristics defined in Premo Specification | R&D
| 1.12 | Feasibility Study (included in PDCC) | [5 empty] | Feasibility tab in PDCC filled | Project Team
| 1.13 | Open Issues List reviewed | [5 empty] | Check that the the Open Issues List (LOP tab) has been reviewed and the tasks are on time. | Project Manager | X
| 1.14 | Risk Assessment & Lesson Learnt Review | [5 empty] | Risk assesment tab in Project_information.xls | Project Manager | X
| GATE RELEASE RESULT |  |  | GATE VALIDATION TEAM: |  |  |  |  | GATE VALIDATION COMMENTS
| Release Status: |  | Open | R&D Resp | Sales Resp
| Released by: |  |  | Engineering Resp | Sourcing Resp
| Release Date: |  |  | Quality Resp | Project Manager
2 | DESIGN VALIDATION (PRODUCT DESIGN & DEVELOPMENT) | [6 empty] | Evidence | Responsible | Yes | Status | Evidence (short link) | Remarks / Gaps | Defined Actions
DV Design Validation | 2.1 | DFMEA | [5 empty] | DFMEA Creation/Update in SkillFMEA. Includes SC/CC (critical characteristics) | Project Team (leaded by R&D)
| 2.2 | PREMO Specification (including packaging definition) | [5 empty] | PREMO Specification approved by Quality in Master List. Includes SC/CC (critical characteristics) | R&D | X
| 2.3 | PREMO Raw Material specifications | [5 empty] | Premo RM Specifications approved by Quality in Master List. Includes SC/CC (critical characteristics) | R&D | X
| 2.4 | Proto-type build Control Plan and Working Instruction (automotive projects with prototypes) | [5 empty] | Protype Control Plan and Working Instruction for DV Samples (applicable only for automotive projects when prototypes are required). Includes SC/CC (critical characteristics) | Engineering
| 2.5 | Design Verification (Samples Inspection Report / SIR) | [5 empty] | SIR for DV Samples | Engineering | X
| 2.6 | Definitive Special Product and Process Characterisitcs | [5 empty] | Updated List of Special Characteristics (if required by customer) in Quality folder OR Characteristics defined in Premo Specification | R&D/Engineering
| 2.7 | Customer Requirements Check List or PREMO Specification acceptance, Customer Specific Requirements cross checked. | [5 empty] | Customer Requirement Form (Premo template or customer template) OR Premo specification accepted by customer (signature or email); Check all Customer Requirements. | Project Quality (supported by Project Team) | X
| 2.8 | BOM with definitive suppliers | [5 empty] | BOM with definitive suppliers form | Sourcing | X
| 2.9 | Suppliers Approval Plan (for non-approved suppliers) | [5 empty] | Review that all suppliers are approved. If supplier is not approved, approval plan is needed. | Sourcing (supported by SQA) | X
| 2.10 | RM PPAP are requested in VEGA | [5 empty] | Projects are opened in VEGA | Sourcing | X
| 2.11 | Preliminary Process Flow Chart | [5 empty] | Preliminary Process Flow Chart file. Includes SC/CC (critical characteristics) | Engineering
| 2.12 | Preliminary PFMEA | [5 empty] | Prelminary PFMEA in SkillFMEA. Includes SC/CC (critical characteristics) | Project Team (leaded by ENG)
| 2.13 | Qualification Test Plan (QTP) is clear and agreed with customer | [5 empty] | Qualification Test Plan (agreed with customer) | Project Quality (supported by R&D and Lab) | X
| 2.14 | New Equipment, Tooling, and Test Equipment Design | [5 empty] | PDCC Reviewed | Engineering | X
| 2.15 | PDCC & Profitability reviewed | [5 empty] | PDCC Reviewed | Project Team (leaded by PM) | X
| 2.16 | Logistics Protocol / Packaging agreement | [5 empty] | According customer request (if required). Sales: collects the information from customer / Supply Chain: evaluation / R&D: Packaging design. | Sales / Supply Chain Manager / R&D | X
| 2.17 | Open Issues List reviewed | [5 empty] | Check that the the Open Issues List (LOP tab) has been reviewed and the tasks are on time. | Project Manager | X
| 2.18 | Risk Assessment & Lesson Learnt Review | [5 empty] | Risk assesment tab in Project_information.xls and Lessons Learnt added in database if proceed. | Project Manager | X
| GATE RELEASE RESULT |  |  | GATE VALIDATION TEAM: |  |  |  |  | GATE VALIDATION COMMENTS
| Release Status: |  | Open | R&D Resp | Sales Resp
| Released by: |  |  | Engineering Resp | Sourcing Resp
| Release Date: |  |  | Quality Resp | Project Manager
3 | INDUSTRIALIZATION (PROCESS DESIGN & DEVELOPMENT) | [6 empty] | Evidence | Responsible | Yes | Status | Evidence (short link) | Remarks / Gaps | Defined Actions
PV Industrialization | 3.1 | PFMEA | [5 empty] | PFMEA in SkillFMEA. Includes SC/CC (critical characteristics) | Project Team (leaded by Engineering)
| 3.2 | Process Flow Chart | [5 empty] | Flow Chart. Includes SC/CC (critical characteristics) | Engineering | X
| 3.3 | Production Plant Layout | [5 empty] | Layout | Engineering | X
| 3.4 | New Equipment, Tooling, and Test Equipment Release | [5 empty] | Equipment list form | Engineering | X
| 3.5 | Pre-Launch Control Plan (if applicable) | [5 empty] | Control Plan. Includes SC/CC (critical characteristics) | Project Quality
| 3.6 | Production Control Plan | [5 empty] | Control Plan (Production) | Project Quality
| 3.7 | SLC Defined & Agreed (if applicable) | [5 empty] | Safe Launch Concept defined in Control Plan (if applicable) | Project Quality (Supported by Project Team)
| 3.8 | Work / Process Instructions (WI and Visual Aids) | [5 empty] | WI and visual aids.Includes SC/CC (critical characteristics) | Engineering | X
| 3.9 | Measurement System Analysis Plan | [5 empty] | R&R/MSA of all testing equipments included in the control plan | Projects Quality (supported by Lab)
| 3.10 | Training matrix definition including training records (if applicable) | [5 empty] | Definition of the training matrix for new production line | Engineering | X
| 3.11 | Incoming Inspection WI / Inspection Plan | [5 empty] | Inspection characteristics defined in SAP | IQC (supported by SQA) | X
| 3.12 | Preliminary maintenance plan (PMP) | [5 empty] | Preventive maintenance plan, instructions, spare parts and records | Engineering | X
| 3.13 | Traceability records | [5 empty] | Definition of the traceability controls (traceability forms, start-up checklist, etc) | Projects Quality
| 3.14 | IQ, OQ, PQ Report | [5 empty] | Installation Qualification (IQ), Operation Qualification (OQ) and Performance Qualification (PQ) checklists available (if applicable) | Engineering | X
| 3.15 | Line Release Report | [5 empty] | Line release report available (Internal audit + Run & Rate) | Project Team | X
| 3.16 | PDCC & Profitability reviewed | [5 empty] | PDCC Reviewed | Project Team (leaded by PM) | X
| 3.17 | Open Issues List reviewed | [5 empty] | Check that the the Open Issues List (LOP tab) has been reviewed and the tasks are on time. | Project Manager | X
| 3.18 | Risk Assessment & Lesson Learnt Review | [5 empty] | Risk assesment tab in Project_information.xls and Lessons Learnt added in database if proceed. | Project Manager | X
| GATE RELEASE RESULT |  |  | GATE VALIDATION TEAM: |  |  |  |  | GATE VALIDATION COMMENTS
| Release Status: |  | Open | R&D Resp | Sales Resp
| Released by: |  |  | Engineering Resp | Sourcing Resp
| Release Date: |  |  | Quality Resp | Project Manager
4 | PRODUCT AND PROCESS VALIDATION | [6 empty] | Evidence | Responsible | Yes | Status | Evidence (short link) | Remarks / Gaps | Defined Actions
PDPV Product & Process Validation | 4.1 | R&R/MSA of all testing equipments included in the Control Plan | [5 empty] | R&R/MSA of all testing equipments included in the control plan | Quality Lab (supported by Project Quality)
| 4.2 | QTP Execution is finished with OK Result | [5 empty] | QTP Execution, Summary results & Reports | Quality Lab (supported by Project Quality) | X
| 4.3 | IMDS is approved by Customer | [5 empty] | IMDS/CAMDS submitted and approved by customer | Project Quality
| 4.4 | Verification of Supplier Approval | [5 empty] | All suppliers approved in VEGA | Project Quality (supported by SQA) | X
| 4.5 | Verification of RM PPAP Approval | [5 empty] | RM PPAP approved in VEGA | Project Quality (supported by SQA) | X
| 4.6 | SPC definition and record (Paretto, %scrap) | [5 empty] | SPC Definition and record (Parettom %Scrap) | Engineering
| 4.7 | Run@Rate with customer | [5 empty] | Run & Rate with customer (if applicable) | Project Team (leaded by PM/ENG/Project QUA)
| 4.8 | PPAP Approval (PSW Signed) - Received & Reviewed | [5 empty] | PSW Signed by Customer | Project Quality
| 4.9 | DFMEA & PFMEA Review after QTP Results | [5 empty] | Review of DFMEA/PFMEA after QTP, in case of failures after test | Project Quality (supported by SQA)
| 4.10 | Line Release Report Review | [5 empty] | Line release report reviewed before project hand over to production (to check possible open points after Stage 3 - Industrialization) | Project Team, Production, Quality | X
| 4.11 | PDCC & Profitability reviewed | [5 empty] | PDCC Reviewed | Project Team (leaded by PM) | X
| 4.12 | Open Issues List reviewed | [5 empty] | Check that the the Open Issues List (LOP tab) has been reviewed and the tasks are on time. | Project Manager | X
| 4.13 | Risk Assessment & Lesson Learnt Review | [5 empty] | Risk assesment tab in Project_information.xls and Lessons Learnt added in database if proceed. | Project Manager | X
| GATE RELEASE RESULT |  |  | GATE VALIDATION TEAM: |  |  |  |  | GATE VALIDATION COMMENTS
| Release Status: |  | Open | R&D Resp | Sales Resp
| Released by: |  |  | Engineering Resp | Sourcing Resp
| Release Date: |  |  | Quality Resp | Project Manager

## IT INFO
PCA
REJECTED
FEASIBILITY
REJECTED
PENDING OFFER ACCEPTANCE
CLOSED LOST
DEVELOPING
CLOSED LOST
SAMPLES
CLOSED WON |  | CLOSED LOST